## Slide 1
Louisiana EPSCoR RII – Track 1
Reverse Site Visit
September 8, 2011

## Slide 2
Welcome from the LA-SiGMA Team
Dr. Randall Hall Chemistry LSU
Dr. Ramu Ramachandran Chemistry LA Tech
Dr. Kerry Davidson Deputy Commissioner LA Board of Regents
Dr. Michael Khonsari LA EPSCoR Project Director Associate Commissioner
Dr. Juana Moreno Physics & CCT LSU
Dr. Henry Ashbaugh Chemical Engineering Tulane

## Slide 3
Project Overview (Michael Khonsari)
Common Computational Tools: The Glue (Randall Hall)
Science Driver 1 (Juana Moreno)
Science Driver 2 (Ramu Ramachandran)
Science Driver 3 (Henry Ashbaugh)
Workforce Development (Juana Moreno)
External Engagement (Ramu Ramachandran)
Diversity (Randall Hall)
Evaluation and Assessment (Henry Ashbaugh)
Sustainability, Management & Impact (Michael Khonsari)
Presentation Outline

## Slide 4
Michael Khonsari
Louisiana EPSCoR Project Director
Associate Commissioner for Sponsored Programs Research & Development
Louisiana Board of Regents
Louisiana’s Research Infrastructure Improvement Strategy 2010-2015
Project Overview

## Slide 5
We are on the cusp of a second Information Technology revolution that in the words of Arden Bement*
*Cyberinfrastructure: The Second Revolution, Chronicle of Higher Education, Jan 3, 2007
“…will dwarf, in sheer transformational scope and power, anything we have yet experienced in the current information age.”

## Slide 6
At the heart of this revolution is peer-to-peer collaboration, new modes of research and education, and virtual organizations that work across institutional boundaries.
This is the premise of our RII research.
Notes: 6

## Slide 7
LA EPSCoR & Board of Regents
Claiborne Building
Baton Rouge, LA

## Slide 8: S&T Framework and Alignment
Foundational Sciences
PHYS
CHEM
MATH
ECON
& SS
BIOL
ENGR
COMP
SCI
EARTH
SCI
AGRI
SCI
BIOM
SCI
21st Century Building Blocks
Atoms & Molecules
Bits & Bytes
Nucleic & Amino Acids
Core Enabling S&T Research
Computational Science Information Technology
Bioscience
Biotechnology
Materials Science
Nanotechnology
High Growth Target Industry
Cyber
Security
Bioengineered
Solutions
Biomedical
Digital
Media
Coastal
Resilience
Energy
Production
Materials &
Chemicals
Translational Research Domains
Environmental
Digital
Coastal
Biomedical
Agricultural
Energy
Core Industry S&T Sectors
Transport, Constr & Mfg
Health
Care
Info Tech & Services
Arts &
Media
Agriculture &
Bio Prod
Energy &
Environ
Petrochem
Aerospace

## Slide 9
LA EPSCoR: Catalyst for Collaboration
LA EPSCoR has broken down boundaries between campuses.
LA EPSCoR is a proven catalyst for achieving increased statewide collaboration and national competitiveness.

## Slide 10
Louisiana Optical Network Initiative (LONI) and Statewide LONI Institute

## Slide 11
NSF RII Award (2010-2015)
Statewide Research Focus
Establishment of…
Notes: 11

## Slide 12
Participants: 179 partners
54 Faculty
5 Post-Doc
18 Technical / Non-Technical Staff
44 Graduate
58 Undergraduate
Notes: 12

## Slide 13
Partnering Institutions
RUSTON
BATON ROUGE
NEW ORLEANS

## Slide 14
LA-SiGMA Vision
To make transformative advances in materials science research and education through a sustained multi-disciplinary and multi-institutional alliance of researchers.
Notes: 14

## Slide 15
Realizing the Vision
Science Drivers
Cyberinfrastructure & Common Computational Tools
Diversity
Year 1 Activities: On Target and On Time
Strategic Planning
Recruitment
Diversity Advisory Council
External Review Board
Initiate Research
Delivery of Courses
Strategies
Workforce Development
External Engagement
Sustainability
Industrial Liaison Committee

## Slide 16
Addressing multiscale complex phenomena calls for:
Scientific and Technological Challenges
Unprecedented collaboration of computer scientists, applied mathematicians, scientists, and engineers with expertise at each scale from sub-nanometer to millimeters in length and from femtoseconds to several seconds in time.
Notes: 16

## Slide 17
Testable Predictions
Refinements to
methods & models
COMMON COMPUTATIONAL TOOLS
Monte Carlo Methods
Density Functional Theory
Molecular Dynamics
Shared Experimental Facilities
Advanced Materials Research Institute
Center for Advanced Microstructures & Devices
Institute For Micromanufacturing
AMRI UNO
IfM LA Tech
CAMD
LSU
Common Computational Challenges and Barriers
Multiple length & time scales, multiscale interactions & correlations
Science Drivers
Correlated Electronic Materials
Energy Materials
Biomolecular Materials
Formalisms, Algorithms, and Codes

## Slide 18
Computational Teams
Cybertools/Cyberinfrastructure
CTCI
Randall Hall
“The glue”
Develop and experimentally validate common computational tools essential for three Science Drivers

## Slide 19
Based on slide from D. P. Landau, UGA
Formalisms, Algorithms, & Codes (FAC)
FAC for new computer architectures (GPUs)
FAC for accurate calculations and simulations (Density Functional Theory & Force Fields)
Throughput (Execution Management)
HD synchronous video for collaboration
Formalisms, Algorithms, Codes, and Technology
Challenges: Time scales, Length scales, & Accuracy
Computer Speed
Complexity
Advances in formalisms, algorithms, and codes are mainly responsible for the increase in the size and complexity of problems we can study.

## Slide 20
CTCI Research Themes
Density Functionals
Grambling, LA Tech, LSU, Southern, Tulane
GPU Programming
LA Tech, LSU, UNO
Force Fields
LA Tech, LSU, Tulane, UNO
Execution Management
LA Tech, LSU
CTCI Teams

## Slide 21
A novel collaboration of 25 faculty, students, and postdocs from LSU, LA Tech, UNO, and Louisiana School for Math, Sciences and the Arts (HS and RET/REU). Using the Collaboratorium* at LSU.
NSF Software Infrastructure for Sustained Innovation (SI2) proposal has been submitted.
GPU Programming
*This room was initially renovated as part of an NSF-supported IGERT at CCT.
~130 Tflops would have been 3rd most powerful computer in the world Nov. 2007.
LA-SiGMA to purchase GPU nodes on LSU’s flagship computer in Fall 2011.
GPU Programming Team
LSU “Condo”

## Slide 22
Scaling of Multi-Scale Methods to 30,000 Cores
Interdepartmental collaboration at LSU develops a latency hiding technique.
Solving the Parquet Equations for the Hubbard Model beyond Weak Coupling, K. Tam, H. Fotso, S.-X. Yang, T.-W. Lee, J. Moreno, J. Ramanujam, and M. Jarrell, submitted Physical Review E.
Kraken at the National Institute for Computational Sciences
Result is efficient use of 30,000 or more processors.

## Slide 23
Density Functional Theory
LA-SiGMA member and DFT pioneer John Perdew of Tulane University was elected to the National Academy of Sciences 2011.
Perdew’s election gives LA-SiGMA two National Academy members in the Alliance.

## Slide 24
Molecular Dynamics and Execution Management
Over 10,000 simulation and analysis tasks to study folding of DNA managed using collaboratively developed “ManyJobs” and “BigJobs” software.
LA Tech (Bishop), LSU (Jha)
Nucleosomal DNA: Kinked, Not Kinked or Self-Healing Material?, R. Mukherjee and T. Bishop, ACS Books, “Frontiers in Nucleic Acids”, under revision.
Publically available execution management tools.
Running Many MD Simulations on Many Supercomputers, R. Mukherjee, H. Fujioka, A. Thota, T. Bishop, S. Jha. In preparation.

## Slide 25
Leveraging LONI Facilities
LA-SiGMA investigating collaborative (LONI, BOR) solutions for HD synchronous video, lecture/seminar capture, and digitization.
Will bring HD and video capture to the State.
LA-SiGMA REU panel
Notes: QB 5540/2, Dell 3072, IBM 416=54.85 M SU’s 41.1M in the 3Qs. 7.3/41.1 = 18%
Rwh 0.160 M Sus Collin 0.300 M Sus Hank 0.100 M SUs Steve R. 0.005 Sus Tom B 0.300 M Sus Lawrence 1.3 M
Ramu .875 M Sus Daniela 0.100 M Sus David 0.200 M, Mark/Juana 4M
Running total 7.34 M

## Slide 26
http://www.cct.lsu.edu/NSF_DataManagement_Plan
http://www.uno.edu/orsp/ORSPHome/ProposalDevelopment/DataManagement
Immediate
Website
Short Term
Modules on the CCT SVN
Long Term
Data repository with Metadata and Search Engine
Data Management
Not required for this RII.
UNO has a local implementation of Digital Commons.
LONI is developing a plan, first report due mid-September.
CCT at LSU and Tulane are developing plans; LA-SiGMA team members at SUBR and Xavier may collaborate with CCT on these plans.
Notes: Rwh 0.160 M Sus Collin 0.300 M Sus Hank 0.100 M SUs Steve R. 0.005 Sus Tom B 0.300 M Sus Lawrence 1.3 M
Ramu .875 M Sus Daniela 0.100 M Sus David 0.200 M, Mark/Juana 4M
Running total 7.34 M

## Slide 27
Cyberinfrastructure Milestones
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Leverage LONI | X | X | X | X | X
Build on CCT/Cybertools | X | X | X | X | X
Migrate to Leadership Class Machines |  |  | X | X | X
Expand LA-SiGMA impact via codes |  |  | X | X | X
On Track
On Track
Ahead
More GPU expertise and more applied math, 3 faculty depart.
Adding 2 GPU experts; in discussion with applied mathematicians.
Challenges/Barriers:
Mitigation plan:

## Slide 28
FOCUS 1
Multiscale Methods for Strongly Correlated Materials
FOCUS 2
Correlated Organic & Ferroelectric Materials
FOCUS 3
Superconducting Materials
Low Energy Electron Diffraction
New FOCUS
SD1: Electronic and Magnetic Materials
Juana Moreno
Extend local approximations [Density Functional Theory (DFT) and Dynamical Mean Field Approximation (DMFA)] to multi-scale approaches

## Slide 29: We need faster, smaller, more efficient chips
By 2020 a transistor in a chip may reach the size of a few atoms.
Devices based on a new paradigm are needed!
Materials Today

## Slide 30
Strongly Correlated Systems:
Complexity and Competing Orders
Competing phases emerge as a function of control parameter.
Electron correlations at different length scales.
Correlations lead to complex spin, charge, and orbital phases.
Tunability allows device applications.
Electrical control of
magnetization
H. Ohno et al., Nature (2000)

## Slide 31
SD1 Research Themes
Organic & Ferroelectric Materials
Tulane, LA Tech, Grambling, UNO, Xavier, LSU
Development Multiscale Methods
Tulane, LSU
Superconducting Materials
Southern, LSU, Tulane
Electronic & Magnetic Materials
Metalloporphyrins
Oxide clusters
Multiferroic composites
Non-local Approximations for DFT
Multiscale Many-Body approach
Iron-based superconductors
Cuprate superconductors
Inverse LEED method for structural investigations

## Slide 32
Dual Fermion Dynamical Cluster Approach for Strongly Correlated Systems, S.-X. Yang, H. Fotso, H. Hafermann, K.-M. Tam, J. Moreno, T. Pruschke, M. Jarrell, arXiv:1104.1739.
Solving the Parquet Equations for the Hubbard Model beyond Weak Coupling, K.M. Tang, S.-X. Yang, H. Fotso, J. Moreno, J. Ramanujam, M. Jarrell. In preparation.
QMC for short length scales
Dual-Fermion diagrammatics for intermediate length scales
Mean-field approximation for long length scales
QMC scales exponentially with problem size, while Multi-Scale Many-Body scales algebraically.
Focus 1
Computing at the Petascale: Multiscale Many Body
MSMB could lead to simulations of electronic and magnetic materials with predicted capabilities.
Notes: 32

## Slide 33: SD1 Focus 1 Milestones
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Develop continuous time QMC solver for 16-way multicore supercomputers. | X | X |  |  | 
Incorporate Hyper-GGA functionals into common DFT codes including VASP. |  | X | X |  | 
Develop MSMB solver able to treat multiple correlated orbitals. |  | X | X | X | 
Port hyperparallel codes to NSF national leadership class machines (Blue Waters). |  |  | X | X | X
On Track
Ahead
Ahead
Ahead

## Slide 34: Focus 2 Iron Oxide Molecular Clusters as Building Blocks of Non-Volatile Memory (Xavier, Tulane, UNO)
Computational/Experimental effort to synthesize spinel-type iron oxide clusters, and investigate their ground state using QM/MM approach.
Co2Fe6H24O24 cluster. Spinel-type structure with water ligands.
Elementary clusters derived from spinel-type structures are candidates for molecular magnets which can be used for high capacity memory devices.
Notes: Our groups are engaged in developing novel techniques for the synthesis, fabrication and characterization of two-phase multiferroic materials with different connectivity schemes. Two-phase ME nanocomposite with different architectures, such as core-shell nanoparticles, nanocables and thin film structures are fabricated by a combination of chemical and physical methods. These efforts are complemented by modeling studies aimed at understanding the role of the shared interfaces on the ME coupling in these nanocomposites. By optimizing their morphology and connectivity schemes, our goal is to maximize the coupling between the ferroelectric and magnetostrictive phases and, ultimately, enhance the ME response at room temperature.

## Slide 35
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Test array of DFT functionals for prediction of metalloporphyrin and ferroelectric properties. | X | X |  |  | 
Prepare and measure electrical/magnetic properties of metalloporphyrin nanostructures. | X | X |  |  | 
Prepare organic magnets and ferroelectrics. | X | X | X |  | 
Develop experimentally validated computational models for porphyrin systems using magnetoresistance and electrical conductance measurements as guides |  | X | X | X | X
Develop multiscale models of metalloporphyrin systems using DFT parameters |  |  | X | X | X
Predict charge transport in metalloporphyrins and compare with experiments |  |  | X | X | X
Predict properties of ferroelectrics using new nonlocal meta-GGA DFT functionals |  |  | X | X | X
Develop experimentally validated models of organic magnets and ferroelectrics |  |  | X | X | X
SD1 Focus 2 Milestones
On Track
On Track
On Track

## Slide 36
What is the pairing mechanism in pnictides?
Tulane/UNO collaboration: Unusual interplay between magnetism and superconductivity in iron chalcogenide Fe1.02 (Te1-x Sex )
Liu et al., Nature Materials 9, 716 (2010).
Bulk superconductivity occurs only when the (π, 0) magnetic correlations are strongly suppressed and spin fluctuations near (π, π ) become dominant.
Focus 3
Superconducting Materials

## Slide 37: New Focus Low Energy Electron Diffraction: An Inverse Problem for Structural Determination (LI/LA-SiGMA seed funded)
Surface Probe: I vs. V curves contain structural information.
Manuel at SURF, LSU
Better inverse problem techniques will improve material characterization
Since new complex materials have many atoms in the unit cell, extracting the structure is computationally challenging.

## Slide 38
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Address the bottlenecks and numerical instabilities in the parquet equations by employing better parallel linear systems solvers and develop multiband parquet codes. | X | X | X | X | X
Incorporate Ramanujam’s advanced tensor rotation and contraction methods (Tensor Contraction Engine) into parquet codes. | X | X |  |  | 
Use hybrid QMC to address the origin of the QCP and competing order in cuprate models. | X | X |  |  | 
Study overscreening in pnictide models using new Hyper-GGA functionals. | X | X | X |  | 
Use methods that combine LDA models obtained from downfolding and DCA/MSMB to study correlation and phonon effects in the pnictides. | X | X | X | X | X
SD1 Focus 3 Milestones
On Track
On Track
Behind*
On Track
On Track
Additional time was required to test the Hyper-GGA functional before porting it to Solid State codes.
Testing is almost complete & porting will take place in the 2nd year of the award.
*Challenge/Barrier:
Mitigation Plan:

## Slide 39
Lithium ion batteries
FOCUS 1
Electrochemical capacitors and fuel cell electrodes
FOCUS 2
Hydrogen Storage Materials
FOCUS 3
Catalyst Materials
New FOCUS
SD2: Energy Materials
Ramu Ramachandran
The goal of this SD is to use DFT functionals, reactive force fields, and Monte Carlo and Molecular Dynamics methods to study materials for the generation, conversion, and storage of energy.

## Slide 40
The July 14 report in Road & Track magazine almost completely captures the foci of Science Driver 2
1905: Energy sources: Electricity, Steam, Gasoline
Environmental Concern: Horse manure
2011: Energy sources: Electricity, Hydrogen, Alternate Fuels
Environmental Concern: Green House gases

## Slide 41
SD2 Research Themes
Hydrogen Storage
LA Tech, LSU
Electrochemical
Tulane, UNO, LA Tech, Xavier, LSU
Metal Oxide Catalysts
LA Tech, LSU, Xavier
Energy Materials
CNT forest-based supercapacitors
Lithium ion batteries
Role of dopants in metal hydrides
Direct imaging of H2 storage materials
Transferable force fields for metal oxides
DFT studies of catalytic reactions
Plans to develop reactive force fields

## Slide 42: Focus 1 Electrochemical capacitors and fuel cell electrodes
Realistic simulations of the role of molecular interactions in electrochemical capacitance are rare.
Intrinsic (or quantum) capacitance depends on electron correlation effects that have been neglected in historical discussions of this phenomenon.
Novel aspect:
Focus on the energetics allows intrinsic capacitance to stand out, helping to shed light on its dependence on quantum aspects like electron correlation.
G. G. Hoffman, L. R. Pratt, X. You & N. Pesika (Tulane), S. W. Rick & R. Mariano (UNO).

## Slide 43: Interplay between experiment and modeling
Initial computations suggest that the filling of nanotube forests by propylene carbonate (PC) is thermodynamically unfavorable. This is contradicted by experimental results.
Problem traced to poor representation of long range (dispersion) interactions in DFT functionals.
The PBE-D dispersion functional is now being employed to study liquid propylene carbonate. Running on Kraken using Teragrid support.
An example of interplay between experiments and modeling.
The role of long-range interactions and electron correlation in electrochemical capacitance models being clarified.

## Slide 44: SD2 Focus 1 Milestones
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Simulation of pore filling in nanowire capacitors . | X | X |  |  | 
Study chemical damage at elevated electric potentials. | X | X | X |  | 
Optimize computational efficiency of ab initio MD techniques. | X | X |  |  | 
Study role of quantum capacitance in electrochemical capacitance. |  | X | X | X | 
Explore additional nanoforest-based capacitor systems. |  |  | X | X | X
Predict catalytic sites in nanotubes. |  | X | X | X | X
Design, build, and test fuel cells and use results to guide new calculations. |  |  | X | X | X
On Track
On Track
On Track
Ahead

## Slide 45: Focus 2 Hydrogen Storage Materials
Structure and Dynamics
Cohesive energy
Preferred Dopant site
Kinetics
Rate-limiting steps in decomposition
Role of dopant
Thermodynamics
Formation of alloys
Reaction Pathways
Many challenges have to be overcome to make hydrogen a viable alternative fuel. Progress in the past decade has been disappointing.
The most important: finding materials with favorable hydrogen absorption and desorption characteristics.
We are developing multi-scale approaches coupled with direct imaging to understand how dopants influence the relevant properties of candidate materials.

## Slide 46: Role of dopants in complex metal hydrides
Plane wave DFT methods are used to study the effect of transition metal dopants on light metal hydrides.
Titanium is found to be the best dopant.
Novel aspects:
Detailed understanding of the role of dopants and adsorption sites in complex formation (e.g., TiMgH3 vs TiMgH7), percolation of H atoms in the lattice, and hydrogen desorption energies.
X-ray and neutron tomography of complex metal hydrides in real time show activity of various sites – to be compared with simulations.
K
Mg
H
Grand canonical ensemble simulation of KMgH3; LSU (Hall, Chen) & LA Tech (Mainardi).
(Na/K)MgH3
Synergy between real-time imaging and simulation leading to an improved understanding of complex metal hydrides.

## Slide 47: SD2 Focus 2 Milestones
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Extend MC methods to calculate free energies of H2 uptake in storage materials. | X | X | X | X | X
Use existing force fields to calculate H2 uptake in bulk alloys. | X | X | X | X | X
Develop finite element model to track 3D microstructure evolution. |  | X | X | X | 
Perform X-ray nanotomography imaging of H2 uptake. [Argonne’s Advanced Photon Source (APS), and neutron tomography at NIST] | X | X | X | X | X
Challenge/Barrier:
Mitigation plan:
On Track
On Track
Ahead
On Track
Dobbins (LA Tech; X-ray nanotomography) on extended leave during Y1.
Les Butler (LSU) providing imaging experiments; Will re-evaluate the research direction in Y2 or Y3.

## Slide 48: Focus 3 Catalyst Materials
Metal oxide catalysts are critical for Fischer-Tropsch type reactions that lead to energy-dense liquid fuels from low energy density feedstock.
Also interested in metal oxide nanocluster catalytic processes that result in polyaromatic species that pose serious health risks.
Need catalyst force fields that can be coupled to reactants and products.
Need reactive force fields to study reactions on the surfaces at large enough length and time scales.
Al2O3
Fe2O3
FeO

## Slide 49: Force field development for metal oxide catalysts
Several DFT-based force fields (nonreactive) currently under development.
DFT studies of catalytic reactions also underway to guide reactive force field development.
Novel aspect:
Empirical Valence Bond (EVB) theory to construct reactive force fields.
Expect simpler development and smoother potentials than the ReaxFF approach of the Goddard group (Caltech).
Multi-state EVB reactive potential for hydrogen transfer from H3O+ to either of two hydrogen-bonded H2O molecules (Wick, LA Tech).

## Slide 50: Catalytic reactions studied by DFT methods
CO2 reduction by H2O on Titania (TiO2) and Zirconia (ZrO2) surfaces studied using plane wave DFT/LDA:
  MS thesis directed by Mainardi (LA Tech).
  Both catalyze the reaction CO2 + 2H2O  HCO2H + 2 OH
  Reaction barrier on TiO2 is lower.
  Calculated reaction paths can guide reactive FF development.
Formic acid formation on TiO2.
Greater insight into catalytic reactions for generating liquid fuels.
Close collaboration with two local companies: Carbon Capture Energy Technologies, and Avoyelles Renewable Fuels, Inc.

## Slide 51: SD2 Focus 3 Milestones
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Develop force fields for one metal oxide system. | X |  |  |  | 
Study water gas shift and Fischer-Tropsch reactions. | X | X | X |  | 
Study persistent free radicals production on metal oxide clusters. | X | X |  |  | 
Develop new force fields and study of additional catalytic processes. |  | X | X | X | 
Validate force field calculations with experimental measurements and DFT calculations. |  |  | X | X | X
Behind schedule on Milestone 1.
LA Tech will hire a postdoc in Y2 who will play a key role in the development of metal oxide force fields.
Challenge/Barrier:
Mitigation plan:
Behind
On Track
On Track
Ahead

## Slide 52: New Focus: Lithium Ion Batteries
Real-time tomography (Butler; LSU) provides images of electrode changes during charge/discharge cycles of lithium ion batteries.
MD studies of ion transport and the role of acidic and basic electrode surfaces under way (Wick; LA Tech).
Experimental and computational studies of metal oxide cathode reactions in early stages. [Funded by non-LA-SiGMA source: Meda –Xavier; Wick, Ramachandran – LA Tech)
Novel aspects:
Potential to develop detailed models of transition metal oxide cathode reactions.
Greater understanding of lithium ion intercalation and chemical damage.
Basic
Acidic

## Slide 53
FOCUS 1
Unimolecular Delivery Vehicles
FOCUS 2
Self-Assembled Delivery Vehicles
SD3: Biomolecular Materials
Henry Ashbaugh
Multi-scale simulation and synthesis of self-assembled and supramolecular drug delivery vehicles.

## Slide 54
extracellular
lipids
corneocytes
The outermost layer of the skin, the stratum corneum, represents the most significant barrier to the transdermal delivery of therapeutics.
2) The primary transport pathway through the stratum corneum involves diffusion through the lipids of the extracellular matrix.
3) The extracellular lipids are organized as multilamellar sheets inhibiting the transdermal diffusion of polar compounds.
The Problem: Skin Physiology

## Slide 55
75nm
Self- Assembled Drug Delivery Vehicles (Focus 2)
- Use self-assembled liposomes to transport polar drugs through lipid channels
- Amphiphiles selected to enable the liposomes to readily deform: transfersomes, ultradeformable liposomes, ethosomes.
200nm
75nm
Drugs
The Problem: Delivery Vehicles
Cons: - Assembly size dictated by thermodynamics
- Assemblies disaggregate below CMC
Pros: - Tunable assembled structures
- Inexpensive
Unimolecular Drug Delivery Vehicles (Focus 1)
Pros: - Robust covalent assembly
- Vehicle size tunable from
5 nm to 50 nm
Cons: - Complex synthesis
- Expensive
Explore Synthesis and Delivery with Both Classes of Vehicles to Optimize Design

## Slide 56
SD3 Goals
linear
star/dendrimer
coarse-grained star
Polymeric Unimolecular
Drug Delivery Vehicles
Self-Assembled
Drug Delivery Vehicles
t = 18 ns
lipid bilayer
Surfactant micelles
Carrier sizes (1 to 100nm), time scales for assembly/delivery (milliseconds or more), accurate free energy evaluation, efficient use of computational resources
Develop novel biomolecular materials guided by computational/experimental collaboration for the encapsulation, delivery, and release of therapeutics to targeted tissues.
Goal:
Simulation challenges:

## Slide 57
Force Fields
Tulane, LSU, UNO
Experimental Carrier Design
Tulane, LSU, LSU-Ag, LA Tech
Simulated Carrier Design
Tulane, LA Tech, Grambling, LSU
Large Scale Free Energy Simulations
UNO, LA Tech
Drug Delivery Materials
SD3 Research Themes

## Slide 58
Focus 1
Synthesize modular core molecules and amphiphilic side chains
Grayson (TU)
6-arm core
3-arm core
bifunctional monomer
+
3-arm
Janus star
6-arm
Janus star
or
 | M.W. | PDI
3-arms | 26.0k | 1.41
6-arms | 45.7k | 1.72
Fluorescence intensity
0.0
0.1
0.2
0.3
Rose Bengal concentration (mg/mL)
2x104
3x104
1x104
0x104
CMC = 0.07mg/mL
or
On track to synthesize first Janus polymer unimolecular drug delivery vehicles.

## Slide 59
Neopentane Solubility in Water
Focus 1 and 2
Develop new force-fields for simulating assembly
Ashbaugh (TU), Moldovan (LSU)
D1 dihedral angle
energy (kcal/mol)
Span80 Intramolecular Potential
ab initio
Amber
First simulation model to quantitatively predict how “Oil and Water Don’t Mix”!

## Slide 60
Focus 2
Molecular dynamics simulation of Span80 self-assembly in micelles
Moldovan (LSU), Nikitopoulos (LSU)
Self-assembly of Span 80 into a single micelle
Kinetics of Span80 aggregation
MD simulations performed with GROMACS 4.0 on LONI supercomputers.
Force field parameters for Span 80 were generated using Gaussian, Amber and PRODRG2.5 server.
MD simulations show that at concentrations of 0.25 M Span 80 self-assemble spontaneously into micelles. The self-assembly process occurs in three stages: (i) aggregation in small clusters (~100ps); (ii) ripening stage, larger clusters grow at the expense of small ones; (iii) diffusion and coalescence of larger clusters.
Time evolution of the number of Span 80 clusters supports the three stage self assembly mechanism.
NSpan80 = 125
t = 100 ps
(a)
t = 18 ns
(b)
Chart: time [ps]
Span80 model applicable to modeling oil spill clean up with dispersants in the Gulf of Mexico

## Slide 61
Moving Wall (impulsively started)
Pure CFD
(no-slip)
Hybrid CFD
Hybrid MD
Developed a general hybrid MD/continuum code for simulating non-equilibrium flows using LAMMPS (MD) and ANSYS/Fluent (continuum)
Extensively tested code for impulsively started Couette flow for Lennard-Jones Fluid
Established collaboration with Dr. Steve Plimpton (Sandia) to distribute through LAMMPS
Focus 1 and 2
Develop hybrid MD/continuum techniques for accelerating time
Moldovan (LSU), Nikitopoulos (LSU)

## Slide 62
SD3 Milestones
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Synthesize modular library of core monomers to explore novel encapsulation/delivery chemistries | X | X | X |  | 
Develop new atomic and coarse-grained force fields | X | X |  |  | 
Develop new hybrid MD/continuum, coarse-grained, and accelerated strategies to link length/time scales | X | X | X |  | 
Use multi-scale simulation methods to optimize supramolecular delivery vehicles |  |  | X | X | X
Synthesize, characterize, and assess new self-assembled transmembrane drug delivery vehicles | X | X | X |  | 
Validate computational models for self-assembled drug carriers for bio-membrane translocation |  |  | X | X | X
Use MD and CG methods to study the mechanisms of cellular absorption of drugs |  |  |  | X | X
On Track
On Track
On Track
On Track

## Slide 63
Traveling the STEM Pipeline
SURE
REU
LINK
SoS
LINK
Planning Grants
Pfund
SBIR/STTR
TGEF
OPT-IN
Programs
Tenured Faculty
K-12
Undergrad / Graduates /Post Docs
Tenure-Track Faculty
Notes: 63

## Slide 64
Workforce Development
Juana Moreno
LA-SiGMA will address all levels of the educational ladder, contributing to a well-trained and diverse professional workforce.

## Slide 65
Workforce Development Strategies
4-Year College Students
Post Docs
2-Year College Students
Graduate Students
High School Teachers
Grades 6 – 12 Students
2-Year College Instructors
Workforce Strategies

## Slide 66
Two graduating Louisiana School for Math, Science, and the Arts were selected to participate in the LSU REU program.
LA Tech/Grambling Open House
Tulane Open House
Grades 6-12
Notes: 66

## Slide 67
Partnerships

## Slide 68
Leveraged LSU’s LaMSTI teacher program
SU RET teachers participated in the GPU team
29% women, 14% URM
High School Teachers
Notes: 68

## Slide 69
30 LASiGMA REU students statewide
46.5% women, 53.5% URM
Undergraduates
Notes: 69

## Slide 70
Supervised Undergraduate Research Experiences (SURE)
SURE is one of the many programs administered by Louisiana EPSCoR. The program, restricted to women & URM, provides a stipend of $4,000/term.
In Year 1, 127 applications were received
30 awards were made.
Another round is expected in December 2011.
Undergrad / Graduates /Post Docs
Notes: 70

## Slide 71
Graduate level courses:
1 course Fall 2010, 3 courses Spring 2011, 2 courses Fall 2011
(4 of the courses in partnership with German & Swiss Universities leveraging PIRE award)
Graduate Students
Notes: 71

## Slide 72
Density Functional Workshop, Summer 2011 (40 registrants, 5 speakers, LA Tech, LSU, SUBR, Tulane, Xavier)
Graduate Students and Postdocs
Indo-US joint proposal being developed.
John Perdew
Tulane
Mel Levy
Tulane & N.C. A&T
Tanusri Saha-Dasgupta
S.N. Bose National Centre
Weitao Yang
Duke
Kieron Burke
UC Irvine
Shobhana Narasimhan
Jawaharlal Nehru Centre
Notes: 72

## Slide 73
Workshop on Computational Thinking
Graduate Students and Postdocs
Computing education for the 21st century proposal with Shodor in the works
Notes: 73

## Slide 74
Workshops on GPU Algorithms and Programming Tools
Graduate Students and Postdocs
Notes: 74

## Slide 75
Materials Science PhD Programs
LSU-SU-UNO joint PhD in Materials Science & Engineering: Proposal approved by SU and LSU systems, being considered by the Louisiana Board of Regents.
LA Tech PhD in Molecular Science & Nanotechnology: Letter of Intent being reviewed by University of Louisiana System, should go to Board of Regents in September. Expect to receive permission to submit proposal for the degree.
Graduate Students
Notes: 75

## Slide 76
Supada Loasooksathit from LA Tech spent one quarter at University of Hertfordshire in the UK
Marielle Soniat from UNO visited Susan Rempe at Sandia Albuquerque
Internships
Graduate Students and Postdocs
Chinedu Ekuma from LSU will visit Pacific Northwest National Laboratory in August 2011
Chinedu Ekuma and Ryky Nelson from LSU will visit Brookhaven National Laboratory in September
Notes: 76

## Slide 77
Links with Industry and National Laboratories (LINK)
Funding to visit and train at an industrial facility, research center, or national laboratory for a period of 2 – 12 weeks.
10 LINK awards:
9 faculty
6 graduate students
University of Aberdeen, Scotland
Los Alamos National Laboratory
Mathematisches Forschungsinstitut, Oberwolfach, Germany
Terrestrial Microbial Ecology Lab, Kyoto University, Japan
World Vegetable Center, Taiwan
Proyecto Yacare, Argentina
Smithsonian Tropical Research Institute, Panama
Tenured Faculty
Undergrad / Graduates /Post Docs
Tenure-Track Faculty
Notes: 77

## Slide 78
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Open House for MS/HS | X | X | X | X | X
Research Experiences for Teachers | X | X | X | X | X
Research Experiences for Undergraduates | X | X | X | X | X
Graduate Courses via Synchronous Video | X | X | X | X | X
Internships at National Labs/Industry | X | X | X | X | X
Graduate Curricula |  | X | X | X | X
Short Courses and Modules for CC | X | X | X | X | X
On Track
On Track
Workforce Development Milestones
On Track
Ahead
On Track
On Track
On Track

## Slide 79
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Summer Workshops for HS/MS | X | X | X | X | X
Beowulf Boot Camp for CC | X | X | X | X | X
Effective Teaching Workshops for GS/PD | X | X | X | X | X
Behind
Behind
Behind
Workforce Development Milestones
Logistical issues (e.g., housing minors on campus) hindered HS/MS summer workshops.
BRCC volunteers instructors for Boot Camp unable to participate.
Logistical issues prevented Effective Teaching Workshop.
Year 1 experience with running RET will allow summer workshops in Year 2.
Meet BRCC Science Dean this August and new instructors on Boot Camp.
Effective Teaching Workshop to be presented in Year 2.
Challenge/Barrier:
Mitigation Plan:

## Slide 80
External Engagement
Ramu Ramachandran
[LA-SiGMA] will provide for efficient collection and dissemination of information between participants, the K-12 community, two-year colleges, and the general public.

## Slide 81
External Engagement Strategies
International partnerships
Science museums
Public lectures
Public media
Interaction with NSF
External Engagement Strategies
Local industry
Internal communications

## Slide 82
Public Media
LA-SiGMA featured in EPSCoR newsletters.
Louisiana Public Broadcasting, public lectures, news media, EPSCoR newsletters.
Interview on Public Radio with RET teachers.
Print media stories about LA-SiGMA in North and South Louisiana.
Working with LPB to be featured on “Louisiana: The State We Are In.”
Notes: 82

## Slide 83
Science Museums & Public Lectures
Multiple events in museums at Baton Rouge, and Shreveport
SciPort Museum in Shreveport, South Arkansas Community College.
Balloon Nanotube at the 2011 NanoDays hosted at the Louisiana Art & Science Museum, Baton Rouge.
Girls Learning About Math and Science (GLAMS) at South Arkansas Community College (event targeting local middle & high school girls).
Public lectures and hands-on activities at SciPort Discovery Center, Shreveport.
Notes: 83

## Slide 84
SoS is one of the many programs administered by Louisiana EPSCoR.
The program provides faculty speakers to K-12 schools free of charge.
60 presentations in Year 1 to over 2,200 students
52% females
38% URM
13,000 students reached in the last 5 years.
Public Lectures: Speaking of Science (SoS)
Undergrad / Graduates /Post Docs
K-12
Notes: 84

## Slide 85
Target: Internal Communications
Monthly seminars over Acess Grid and IOCOMM network held all through Year 1.
HD video conferencing equipment being purchased to take advantage of LONI bandwidth.
Web portal operational http://lasigma.loni.org
Leverage cyberinfrastructure, video-conferencing, collaboration tools, web portal, all-hands meetings.
Notes: 85

## Slide 86
Target: Internal Communications
Three meetings held in Year 1, including the 2011 EPSCoR RII LA-SiGMA Symposium.
LA-SiGMA Facebook page.
Leverage cyberinfrastructure, video-conferencing, collaboration tools, web portal, all-hands meetings.
30 contributed papers (posters)
18 multi-campus contributions
90 participants
ERB
DAC
Winners of the poster competition will attend national EPSCoR meeting in Idaho.
Notes: 86

## Slide 87
Target: National and International Partnerships
Indo-US joint proposal being developed.
NSF-G8 Research Councils proposal being developed (LA-SiGMA, Japan, Germany).
Notes: 87

## Slide 88
Partnership with Pacific Northwest National Lab
Environmental Molecular Sciences Laboratory (EMSL)
  Home of NWChem!
DOE INCITE request for 200,000,000 SUs over 3 years on Jaguar and Titan supercomputers (20+ PFLOPs, Kepler GPUs)
EMSL Associate Lab Director Bill Shelton participating in an LA-SiGMA REU panel
Internship program for LA-SiGMA students
  3-6 month visits
  Working with EMSL Open Source Code Developers
  Opportunities for students, undergraduate to PhD
Partners in Indo-US SCES Centre

## Slide 89
Target: NSF
Strategic Planning meeting attended by EPSCoR program director.
Strategic Plan revised with NSF feedback and resubmitted.
NSF invited to RII LA-SiGMA Symposium in August, 2011.
Nine highlights on LA-SiGMA activities submitted in Year 1.
LA-SiGMA RET story featured on NSF website.
Formal mechanisms for interaction with NSF
Notes: 89

## Slide 90
Strategies | Y1 | Y2 | Y3 | Y4 | Y5
Leverage multiple avenues to engage the general public. | X | X | X | X | X
Create a web portal for distribution of project deliverables. | X | X | X | X | X
Create a repository and version control system for code development and distribution. | X | X | X | X | X
Leverage cyberinfrastructure to facilitate communication. | X | X | X | X | X
Use Newsletter/Brochures/Highlights to publicize Alliance activities. | X | X | X | X | X
Create formal mechanisms for engagement with NSF. | X | X | X | X | X
Establish new national and international collaborations. | X | X | X | X | X
Create mechanisms for internal communications. | X | X | X | X | X
External Engagement Milestones
*Mostly on track; pending LPB appearance and HD video conferencing equipment purchase.
Mitigation plan: Working with LPB for feature, HD standards being finalized.
On Track*
On Track
On Track
On Track*
On Track
On Track
On Track
On Track

## Slide 91
Diversity
Randall Hall
Increase the number of URM and women in the Alliance.

## Slide 92
Diversity Strategies
Create pipelines to graduate school
Financial Incentives
Diversity Advisory Council
Develop faculty role models
Diversity Strategies

## Slide 93
Diversity Advisory Council
DAC and LA-SiGMA EEWD Committee members in attendance at the August 2011 RII LA-SiGMA Symposium
LA-SiGMA is acting on the Fall 2011 DAC suggestions.
Notes: #1. Diversity Advisory Council has been established. They meet at the second All Hands Meeting on August 6, 2011
The LA-SiGMA External Engagement and Workforce Development Committee completed a document for the Diversity Advisory Council with existing and planned strategies at each school.
#2. LA-SiGMA announced supplemental research assistantships for women and URM graduate students to all faculty LA-SiGMA members. Since LA-SiGMA funds became available only after October 2011, our Year 1 recruiting efforts were targeted for students who will join us in Year 2.
#3. LA-SiGMA has announced the availability for funds to supplement department start-up packages to LA-SiGMA institutions to recruit new URM and female faculty members with research interests in Materials Science. None hired yet.
Mentoring: None done
#4. Existing 3+2 and 4+1 programs in the state. LA-SiGMA plans to use these pipelines, as well as expand on them in the future.

## Slide 94
Graduate Assistantship Supplements
Announced, targeting Fall 2011 awards
Supplements to Startup Packages
Contributing to the startup package of Anne Robinson, Tulane.
Pipelines
Targeting recruiting efforts in all state bridge programs:
4+1 Grambling/LaTech, 3+2 Xavier/Tulane, 2+2 LSU/BRCC and 2+2 Southern/BRCC beginning Fall 2011
Strategies

## Slide 95
Diversity Milestones
Milestones | Y1 | Y2 | Y3 | Y4 | Y5
Diversity Advisory Council. | X | X | X | X | X
Provide financial incentives to GS. | X | X | X | X | X
Supplement Startup Packages. | X | X | X | X | X
Create/expand pipelines to graduate school. |  | X | X | X | X
On Track
On Track
On Track
On Track
Small pool year 1
Focus on year 2 and beyond
Challenge/Barrier:
Mitigation Plan:
Notes: #1. Diversity Advisory Council has been established. They meet at the second All Hands Meeting on August 6, 2011
The LA-SiGMA External Engagement and Workforce Development Committee completed a document for the Diversity Advisory Council with existing and planned strategies at each school.
#2. LA-SiGMA announced supplemental research assistantships for women and URM graduate students to all faculty LA-SiGMA members. Since LA-SiGMA funds became available only after October 2011, our Year 1 recruiting efforts were targeted for students who will join us in Year 2.
#3. LA-SiGMA has announced the availability for funds to supplement department start-up packages to LA-SiGMA institutions to recruit new URM and female faculty members with research interests in Materials Science. None hired yet.
Mentoring: None done
#4. Existing 3+2 and 4+1 programs in the state. LA-SiGMA plans to use these pipelines, as well as expand on them in the future.

## Slide 96
Evaluation and Assessment
Henry Ashbaugh
Evaluation and Assessment of (1) research milestones; (2) broader impacts; and (3) impact on the jurisdiction’s S&T enterprise.
.

## Slide 97
Evaluation and Assessment Team
External Review Board
External Evaluator
Kansas State University Office of Educational Innovation & Evaluation
Internal Review Board
Dr. Ramu Ramachandran LA Tech
Dr. Cheryl Stevens Xavier
Dr. Scott Whittenburg UNO
Dr. Diola Bagayoko SUBR
Dr. Hank Ashbaugh Tulane
Dr. Shantenu Jha LSU
Dr. William Lester UC Berkeley
Dr. Susan Sinnott University of Florida
Dr. Vincent McKoy Caltech
Dr. Valerie Taylor Texas A&M
Dr. Harold Silverman SUNY (retired)

## Slide 98
Program Evaluation and Assessment
• Logic Models clearly defined inputs, strategies, activities, outputs, outcomes, and metrics for overall project and team goals.
  • Goal-Based Evaluation Work Plan guides the assessment of the impact of team strategies and the broader impacts of the project overall. Each of the nine project team goal areas and strategies contain:
Process
  • Types of data
    Data source (database, survey, interview, document review, focus group)
    Formative and summative metrics from logic models and proposal
  • Strategy to be assessed
  • Method(s) of evaluation (quantitative and qualitative) and timeline
  • Criteria for accomplishment or outcomes desired
  • Responsibility

## Slide 99
Baseline Survey
Time window: Oct. 1, 2009 – Oct. 31, 2010. Deliberately had a small overlap (1 month) with the current project.
The purpose of the overlap was to see how quickly we were able to pick up or transfer students to LA-SiGMA funding.
Survey response rate across the state
93%
Graduate students
Undergraduate students
Diversity in the G and UG populations
External Engagement
Research Productivity – papers, presentations, proposals
Research Collaboration – collaboration tools/mechanisms
Computational Science/Technology utilization
Intellectual Property Development
Goal: Collect statistics for the year prior to LA-SiGMA funding.
The survey covered all aspects of the project:

## Slide 100
Evaluation Plan
OEIE has developed an evaluation plan to assess advancement along Louisiana EPSCoR goals
SD1
Electronic and Magnetic Materials: Model larger lengths scales than currently feasible
SD2
Energy Materials: Computationally model/design next gen energy materials for generation/storage/conversion
SD3
Biomolecular Materials: Model/design novel drug delivery vehicles
CTCI
Computational Teams and Cyber-infrastructure: Develop formalisms, algorithms, codes for leadership class machines
DIV
Diversity: Dramatically increase minority and women representation
EE
External Engagement: Outreach to K-12, community colleges, industry, & public
S/RI
Sustainability – Research Infrastructure: Initiate programs to propel LA researchers to national competitiveness
S/FD
Sustainability – Faculty Development: Effectively compete for federally funded materials center

## Slide 101
Sustainability, Management & Impact
Michael Khonsari
By the end of the RII project, Louisiana will succeed in establishing a federally funded center of excellence such as a MRSEC, ERC, or STC.

## Slide 102
Traveling the STEM Pipeline
SURE
REU
LINK
SoS
LINK
Planning Grants
Pfund
SBIR/STTR
TGEF
OPT-IN
Programs
Tenured Faculty
K-12
Undergrad / Graduates /Post Docs
Tenure-Track Faculty
Notes: 102

## Slide 103
Awards of up to $10,000 to:
Pilot Funding for New Research (Pfund)
Tenure-Track Faculty
Tenured Faculty
Enhance research focus
Explore new ideas
Keep pace with cutting-edge techniques
47 Pfund awards were made this year.
Notes: 103

## Slide 104
Pfund Results: Impact From Previous RII
2008 – 2010 and counting…
2 Patents
205 Publications
251 Presentations
189 Proposals Submitted
41 Proposals Awarded
$16 Million External Funding
Notes: 104

## Slide 105
Build sustainable relationships between academia and industry
Facilitate the commercialization of research
Enhance research competitiveness
Promote the economic development of Louisiana
Opportunities for Partnership in Technology with Industry (OPT-IN)
Tenure-Track Faculty
Tenured Faculty
Category I
Research Focus
Category II
Commercialization Focus
$10,000 – 50,000
Cash Match Required
100% cash match for non-LA industry/private sponsor
8 OPT-IN Awards were made
Notes: 105

## Slide 106
Held in October 2010 in Baton Rouge
Two industry panels
Panel of campus IP officers
Industry-Academia Collaborative Workshops
Materials & Energy
Software Development & Digital Media
Held in June at the LITE Center in Lafayette
3 panels consisting of:
  Industry needs
  The academic perspective
  Stories of successful collaboration
Notes: 106

## Slide 107
Supports the development of projects with economic potential by offering “Phase Zero” awards that assist small businesses to prepare and successfully compete for Small Business Innovative Research (SBIR) or Small Business Technology Transfer (STTR) proposals.
19 SBIR/STTR awards were made in year 1.
SBIR/STTR Phaze Zero Grants
Tenure-Track Faculty
Tenured Faculty
Notes: 107

## Slide 109
RII - Track 1: Management
Michael Khonsari
Project Director
LA EPSCoR Staff
External Review Board (ERB) & External Evaluator
State EPSCoR Committee
Project Execution Team (PET)
Science & CI (S&CI) Leads
Jarrell (LSU), Pratt (Tulane)
External Engagement, Workforce & Diversity Development (EEWD) Leads
Hall (LSU), Derosa (LA Tech/Grambling)
Evaluation & Assessment (E&A) Leads
Ramachandran (LA Tech), Stevens (Xavier)
Science Driver and Computational Teams
Faculty, Students, and Postdocs
ILT Representative
Whittenburg (UNO), Ramachandran (LA Tech)
DAC Representative
Bagayoko (SUBR), Derosa (LA Tech/Grambling)
Industry Liaison Team (ILT)
Diversity Advisory Council (DAC)
Project Execution Team (PET)

## Slide 110
Research
Diversity
At the end of Year 1…
Strong Multidisciplinary and Multi-Institutional Research Teams
Transformative Research and Education in Materials Science
Multi-institutional research teams formed.
Collaboration tools being used to strengthen ties between team members.
Joint papers and proposals already being submitted.
Workforce Development
First year REU and RET programs highly successful.
Plans already in place to involve middle and high school students in research.
Programs for 2-year colleges about to be launched.
New PhD programs in Materials Science and Engineering proposed.
Diversity Advisory Council formed.
Financial incentives for women and URM graduate students being offered.
Programs are ongoing to recruit women & URM at all levels.
SURE Grants awarded.
Notes: 110

## Slide 111
Evaluation and Assessment
External Engagement
Computational Teams & Cyberinfrastructure
On target to meet expected outcomes …
GPU team established.
New hybrid hardware being purchased at LSU (shared resource).
HD synchronous video equipment being purchased.
On track to leverage emerging paradigms in computing.
Multiple avenues and events for public outreach successfully utilized.
Additional public engagements being planned and pursued.
International partnerships established and being formalized through joint proposals.
External evaluator and External Review Board.
Comprehensive evaluation plan established.
Strategic plan prepared, revised, and submitted to NSF.
Strong Multidisciplinary and Multi-Institutional Research Teams
Transformative Research and Education in Materials Science
Multiscale Simulation Tools for 21st Century Computing Environments
National Center of Excellence in Multiscale Materials Simulation

## Slide 112
Collectively we are on track to make transformative
advances in materials science research and education
LA-SiGMA Present and Future
Center of Excellence
Multi-scale simulation tools
Interdisciplinary research groups
Highly trained STEM workforce
Linkages to national labs and industry
Model for collaborative graduate education